PROJECT PLAN & TEAM WORK DIVISION

ChainSync

Blockchain-Based Process Synchronization

Replacing semaphores with blockchain consensus: every critical-section access is validated by agreement among independent nodes

| Team | Tijay · Ujjwal |
| --- | --- |
| Document date | 19 October 2026 |
| Based on | Blockchain Process Synchronization Study Guide (Chapters 15–24) |
| Purpose | Single reference for what we are building, who owns what, how our parts connect, and when each piece is due |

# Contents

1. Project in one page

2. Architecture

3. The lock manager (core specification)

4. Team roles and work division (who does what)

5. How our two halves connect

6. Build plan and timeline

7. Evaluation plan

8. Failure scenarios we must handle

9. Working agreement

10. Optional extensions

11. Risks and open items

# 1. Project in one page

## 1.1 The problem

Several programs, possibly on different machines owned by different organisations, must take turns using something shared (a database row, a file service, a bank account). A normal OS semaphore lives in one machine’s memory, so it cannot help. A central lock server can, but everyone must then trust whoever runs it, and if it fails or cheats the whole system fails or cheats with it.

ChainSync removes the single trusted server. The decision “who may enter the critical section” is made by many independent nodes agreeing through blockchain consensus, and every decision is permanently and verifiably recorded.

## 1.2 The one idea behind the whole design

State Machine Replication. 1. The lock manager is a deterministic state machine: same state + same transaction = same new state, always. 2. The blockchain with consensus makes every node receive the same transactions in the same order. 3. Therefore all nodes always agree on the lock state. Two honest nodes never believe two different processes hold the same mutex.

## 1.3 What replaces what

| Ordinary OS semaphore | ChainSync equivalent | Why |
| --- | --- | --- |
| Integer variable S | Capacity minus number of current holders, kept in the world state | The count is data in the replicated state machine |
| Atomicity from hardware | Single total order of transactions in the replicated log | Consensus picks one winner, as hardware picks one core |
| Kernel queue of blocked processes | FIFO waiting queue inside the lock manager state | Same structure, replicated on every node |
| wait() | ACQUIRE transaction | Granted immediately or queued |
| signal() | RELEASE transaction | Frees a unit and promotes the head of the queue |
| wakeup(P) | GRANTED event delivered to the client | Clients subscribe to events |
| Kernel cleans up dead processes’ locks | Lease expiry decided by agreed block time | Nobody can tell dead from slow, so time limits decide |
| Process ID | Public key (address) of the client | Cryptographic, unforgeable identity |
| No history | Immutable ledger of every grant and release | Audit trail and non-repudiation |
| Trust the kernel | Trust a quorum of validators | No single machine or operator is trusted |

## 1.4 Honest positioning (important for the report and viva)

We do not claim “blockchain is better than etcd”. We claim: when participants distrust one another, or when an auditable history is required, this design gives guarantees etcd does not. The trade-offs are higher latency (milliseconds, not nanoseconds), lower throughput ceiling, and more moving parts to deploy.

| Where ChainSync is stronger | Where it is weaker |
| --- | --- |
| No single trusted operator; suits mutually distrusting organisations | Higher latency than a local semaphore; lower throughput ceiling |
| Tamper-evident, signed audit trail of every lock event | More components to deploy, monitor and secure |
| Can tolerate malicious validators (BFT mode), not only crashes | Adding nodes does not make it faster; scaling needs sharding |
| Non-repudiation: a process cannot deny having held a lock | For one organisation with trusted servers, etcd or ZooKeeper is simpler and faster |

## 1.5 Glossary

| Term | Meaning |
| --- | --- |
| Client / process | Any program that wants to enter a critical section; holds a private key |
| SDK | Library the client uses: acquire(), release(), renew() |
| Gateway | Front door of the cluster: checks signatures and limits, forwards transactions, streams events |
| Node (validator) | One member of the blockchain cluster; runs mempool, consensus, ledger and lock manager |
| Lock manager | The state machine / smart contract that implements semaphore rules |
| Semaphore | A named synchronisation object with a capacity (1 = mutex) |
| Holder | A client currently inside the critical section of a semaphore |
| Lease | Time limit attached to a grant; it expires if not renewed |
| Fencing token | Increasing number issued with each grant, checked by the protected resource |
| Protected resource | The real thing being guarded; it verifies fencing tokens |
| Block time | Timestamp inside the agreed block; the only clock the lock manager reads |

# 2. Architecture

## 2.1 Layers

APPLICATIONS (any machine): P1 P2 P3 ...

|

CLIENT SDK  acquire() release() renew()   [holds private key]

|  signed transactions (gRPC / REST)

GATEWAY  check signature | rate limit | forward | stream events

|

BLOCKCHAIN NODE (run 3, 5 or 7)

Mempool --> CONSENSUS (Raft | PBFT) --> Block builder

|

LEDGER (append-only)      LOCK MANAGER (state machine)

block 0,1,2,...           WORLD STATE DB + EVENTS

Dashboard / block explorer        PROTECTED RESOURCE

(reads ledger and state)          (checks fencing tokens)

| Layer | Input | Output | Guarantee |
| --- | --- | --- | --- |
| Client SDK | acquire("account-42") etc. | Signed transaction; later the result and token | Identity, unique request IDs, retries without double effects |
| Gateway | Signed transactions | Valid transactions to the leader; events to clients | Filters invalid or abusive traffic before it costs consensus time |
| Mempool | Valid pending transactions | Batch for next block | Holding area; deduplicates |
| Consensus engine | Candidate blocks from the leader | One committed block per height | All honest nodes agree on order; deterministic finality |
| Ledger | Committed blocks | Append-only hash-linked history | Tamper evidence and audit |
| Lock manager | Committed transactions in order + block time | New lock state, results, events | Mutual exclusion, FIFO fairness, lease expiry, token issuing |
| World state DB | State changes | Fast lookups of current locks | Current view for queries and dashboard |
| Event emitter | State changes such as GRANTED | Notifications to subscribed clients | Waiting clients learn promptly without polling |
| Protected resource | Requests carrying fencing tokens | Accept or reject | Stops zombie holders corrupting data |

## 2.2 Two data flows

- Write path (a transaction): client → gateway → leader mempool → consensus → every node’s ledger and lock manager → event → client. Expensive because of the consensus round.

- Read path (a query): client → gateway → one node’s world state → client. Cheaper; may be slightly stale unless a linearizable read is requested.

# 3. The lock manager (core specification)

This is the heart of the system and the part both of us must understand, even though Tijay implements it.

## 3.1 Data model

| Field | Where | Meaning |
| --- | --- | --- |
| name | Semaphore | Unique identifier, such as "account-42" |
| capacity | Semaphore | Maximum simultaneous holders (1 = mutex, N = counting semaphore) |
| holders | Semaphore | Set of current grants; each has owner, fencing token and expiry time |
| queue | Semaphore | FIFO list of waiting requests (owner, request ID, requested lease length) |
| next_token | Semaphore | Next fencing token to hand out; only ever increases |
| seen | Global | Set of (owner, request ID) pairs already processed; makes retries harmless |
| acl | Global or per semaphore | Which identities may create, acquire or administer |

## 3.2 Transaction types

| Transaction | Parameters | Possible results |
| --- | --- | --- |
| CREATE | name, capacity (admin only) | CREATED or REJECTED (exists / not authorised) |
| ACQUIRE | name, lease length, request ID | GRANTED(token, expiry) or QUEUED or REJECTED |
| RELEASE | name, token | RELEASED or REJECTED (not owner, token unknown or expired) |
| RENEW | name, token, new lease length | RENEWED(new expiry) or REJECTED |
| TICK | none (sent by the leader periodically) | Advances the chain clock so leases expire even when no clients are active |

## 3.3 Rules that must hold

- wait(S) = ACQUIRE. If a unit is free and nobody is waiting, grant with a new fencing token and lease expiry. Otherwise append to the queue and answer QUEUED.

- signal(S) = RELEASE. Remove the holder, then promote waiters from the head of the queue while capacity is free; each promotion creates a new grant (new token, new expiry) and a GRANTED event.

- Atomicity comes from the total order: transactions run one at a time in log order, so “check free, then take” can never interleave with another request.

- Lease clock = block time only. Never read the machine clock inside the lock manager. Before executing any transaction, remove every holder whose expiry ≤ block time and promote waiters. The leader emits a TICK block roughly every second so abandoned locks are reclaimed.

- Followers accept a block only if its timestamp is greater than the previous block’s and within a small tolerance of their own clock.

- Idempotency: a repeated (owner, request ID) must return the original result and cause no second effect.

- Fencing tokens strictly increase per semaphore and are checked by the protected resource, which rejects any token lower than the highest it has seen.

## 3.4 Properties we must prove and test

| Property | Meaning |
| --- | --- |
| Mutual exclusion | Never more than capacity holders at once; capacity 1 means never two holders |
| Progress | If the lock is free and someone asks, someone gets it |
| Bounded waiting / FIFO | Grants happen in queue order; nobody is overtaken indefinitely |
| Deadlock freedom | Leases guarantee a crashed holder cannot block forever |
| Token monotonicity | Fencing tokens only ever increase |
| Determinism | Replaying the same log gives byte-identical state on every node |
| Linearizability | Whole service behaves like one atomic semaphore |

# 4. Team roles and work division

The work was split by effort, not by headcount of components: each task has an effort score from 1 (small) to 5 (large), and both of us carry 20 points. The split follows the layers of the architecture so each of us can build and test our half without waiting for the other.

|  | Tijay | Ujjwal | Shared |
| --- | --- | --- | --- |
| Role title | Ledger, lock logic and visibility | Consensus, network and performance | Proto, report, viva |
| Focus | What the chain stores and decides | How nodes agree and how clients reach them | Contracts between our halves |
| Effort points | 20 | 20 | n/a |
| Main languages / tools | Python or Go, property-testing library, web UI | Go or Python, Raft library, gRPC, Docker, Prometheus | Protobuf, Git |

## 4.1 Tijay: ledger, lock logic and visibility (20 points)

| # | Task | What “done” looks like | Pts |
| --- | --- | --- | --- |
| T1 | Lock manager state machine (Ch. 17) | CREATE, ACQUIRE, RELEASE, RENEW and TICK implemented as a pure, deterministic function apply(tx, block_time). FIFO queue, capacity, fencing tokens, lease expiry by block time, idempotency via seen set. No network, no clock, no randomness. | 5 |
| T2 | Ledger (Ch. 7, 8) | Signed transactions (Ed25519 or similar), blocks with previous-hash link and Merkle root, persistent storage, replay on restart reproduces identical state. Tampering with any stored block is detected. | 4 |
| T3 | Mempool, dedup and TICK blocks | Pending-transaction pool with dedup by (owner, request ID); leader injects TICK blocks about once per second. | 1 |
| T4 | Property and correctness tests (Ch. 13) | Random transaction sequences never violate capacity, FIFO or token monotonicity. Replay determinism test. Optional: small TLA+ spec of the lock manager. | 3 |
| T5 | Protected resource with fencing | Small storage service that remembers the highest token and rejects older ones; demo of a zombie write being refused. | 1 |
| T6 | Dashboard and block explorer | Web page showing semaphores, holders, queue, lease countdowns, recent blocks, and Merkle proof verification for a transaction. | 3 |
| T7 | Demos (Ch. 4) | Dining philosophers, bank transfer, producer-consumer, each running on ChainSync with no safety violation. | 2 |
| T8 | Conformance test suite | One shared script of client-level tests (acquire, queue, release, retry with same request ID, lease expiry, token order) that runs against both Ujjwal’s mock server and the real node. Passing on both is the proof the swap is safe. | 1 |

## 4.2 Ujjwal: consensus, network and performance (20 points)

| # | Task | What “done” looks like | Pts |
| --- | --- | --- | --- |
| U1 | Consensus layer (Ch. 9, 22.3) | Small interface: propose(block), onCommit(callback), isLeader()/leaderId(). 3-node Raft cluster (library or own), replication, leader election and failover. Killing the leader never loses committed locks and never double-grants. Optional later: BFT adapter behind the same interface. | 5 |
| U2 | Gateway (Ch. 12, 16) | Verifies signatures, rate limits per client, enforces ACLs, routes writes to the current leader, serves reads from a node, streams events. | 3 |
| U3 | Client SDK | Python library: acquire(), release(), renew(). Signs transactions, generates unique request IDs, retries safely (idempotent), waits for GRANTED event. Optional Go version. | 2 |
| U4 | Event streaming | GRANTED / RELEASED / EXPIRED events delivered to subscribed clients without polling. | 1 |
| U5 | Deployment and metrics (Ch. 14) | docker-compose that starts the whole cluster with one command; Prometheus metrics for latency, queue length, block rate. | 1 |
| U6 | Benchmarks (Ch. 23) | Load generator and baselines against etcd, ZooKeeper, Redis (Redlock) and a local mutex on an identical workload; latency, throughput and contention graphs. | 3 |
| U7 | Chaos and failure tests (Ch. 13, 19) | Scripts that kill the leader under load, partition the network (2/1 and 1/1/1), pause clients longer than the lease; record recovery time and safety violations. | 2 |
| U8 | Linearizability / correctness checker | Records every client operation with timestamps, checks the history for mutual-exclusion and linearizability violations (Jepsen-style). | 2 |
| U9 | Mock lock server | Tiny in-memory server that follows proto/ and the section 3 rules (FIFO, increasing tokens, idempotent retries, lease expiry). Lets him build the gateway, SDK and events from day one. Later replaced by the real node via a config change. | 1 |

## 4.3 Shared responsibilities

- Week 1: write and freeze the `proto/` definitions together (transaction format, events, block format, apply(tx, block_time) signature).

- Architecture and threat-model document (Ch. 12): half each; Tijay covers ledger and lock-manager threats, Ujjwal covers network, gateway and consensus threats.

- Final report and viva preparation (Ch. 24): each of us writes up our own half and reads the other’s so either can answer any question.

- Code review: every pull request is reviewed by the other person.

# 5. How our two halves connect

| Interface | Producer | Consumer | Notes |
| --- | --- | --- | --- |
| proto/ (messages) | Both, jointly | Both | Frozen after week 1; changes need both to agree |
| Consensus: propose(block), onCommit(cb), isLeader() | Ujjwal (implements) | Tijay (ledger, mempool call it) | Everything above consensus reacts only to onCommit, so Raft can be swapped for BFT |
| Lock manager: apply(tx, block_time) → (result, events) | Tijay | Node runner and gateway | Pure function; the only entry point to lock state |
| Event stream | Tijay (lock manager emits) | Ujjwal (gateway delivers) | Used by SDK and dashboard |
| Ledger and world-state reads | Tijay | Ujjwal (gateway), Tijay (dashboard) | Read path; supports stale and linearizable reads |
| Mock lock server | Ujjwal | Ujjwal (gateway, SDK), Tijay (conformance suite) | Stand-in for the real node during development; swapped out by changing the gateway’s target address |
| Single-node mode | Tijay | Ujjwal | Consensus stub where propose() commits straight to onCommit(); the real replacement for the mock |

Unblocking rule: nobody waits for the other. 1. After the proto is frozen in week 1, Ujjwal writes a mock lock server (U9) and builds the gateway, SDK and events against it from day one. 2. Tijay builds the lock manager and ledger against a stub consensus (propose() commits straight to onCommit()) and later ships this as single-node mode. 3. Ujjwal develops Raft against a dummy state machine, so he does not need Tijay’s ledger either. 4. When single-node mode is ready, Ujjwal points the gateway at it instead of the mock (a config change). Tijay’s conformance suite (T8) runs against both, so a pass on both means the swap is safe. 5. The two halves meet for real at the consensus interface in Phase 3.

## 5.1 Swapping the mock for the real node

- Keep the mock faithful to section 3: FIFO queue, strictly increasing tokens, idempotent retries, lease expiry. A sloppy mock hides bugs until the swap.

- Run the same conformance suite (T8) against the mock and against single-node mode. Differences show up immediately.

- Swapping in single-node mode gives no consensus yet. Raft arrives in Phase 3 when the ledger and consensus layer are joined.

## 5.2 Suggested repository layout

chainsync/

proto/          protobuf definitions                     (shared)

node/

consensus/    raft adapter, optional pbft adapter      (Ujjwal)

ledger/       block, hash links, merkle, storage       (Tijay)

mempool/      pending tx, dedup, TICK                  (Tijay)

statemachine/ lockmanager, pure and deterministic      (Tijay)

api/          gateway, rate limit, events              (Ujjwal)

sdk/            python client library                    (Ujjwal)

mock/           mock lock server for early development  (Ujjwal)

resource/       protected storage with fencing check     (Tijay)

demos/          philosophers, bank, producer-consumer    (Tijay)

verify/         property tests, tla+, conformance (Tijay); checker (Ujjwal)

bench/          load generators, baseline comparisons    (Ujjwal)

deploy/         docker-compose, metrics                  (Ujjwal)

dashboard/      web UI and block explorer                (Tijay)

docs/           architecture, threat model, report       (shared)

# 6. Build plan and timeline

The guide recommends building in layers and testing each before the next. Phases below are in order; assign calendar dates once the submission and demo deadlines are known (see section 11).

| Phase | Suggested duration | Tijay | Ujjwal |
| --- | --- | --- | --- |
| 0. Learn | Week 1 | Chapters 1–4, 7, 8, 10 of the study guide; run the toy blockchain from section 8.4 | Chapters 5, 6, 9, 11, 12, 14; play with raft.github.io. Both: write proto/ together |
| 1. Lock manager | Weeks 2–3 | T1 lock manager and T4 property tests, no network at all | U9 mock server first (days), then U1 Raft prototype on a dummy state machine; U5 repo and Docker skeleton; U2/U3 gateway and SDK against the mock |
| 2. Single-node chain | Weeks 3–4 | T2 ledger, signatures, replay; T3 mempool and TICK; T8 conformance suite; ship single-node mode | Continue U2 gateway and U3 SDK against the mock; switch target to single-node mode once T8 passes on both |
| 3. Consensus | Weeks 5–6 | Plug ledger and lock manager into the consensus interface; replay determinism across 3 nodes | U1 finished: 3-node Raft, failover; U5 docker-compose for 3 nodes |
| 4. Service layer | Week 7 | T5 fencing resource; lease and TICK integration | U4 events; U2 rate limits and ACLs; SDK retries |
| 5. Demos and visibility | Week 8 | T6 dashboard and explorer; T7 demos | U7 chaos tools; U8 correctness checker |
| 6. Evaluation and hardening | Weeks 9–10 | Correctness evidence, audit-overhead measurements; optional TLA+ | U6 benchmarks and graphs; written analysis of results |
| 7. Report and viva | Final week | Report sections for ledger, lock manager, dashboard | Report sections for consensus, gateway, evaluation. Both: mock viva |

## 6.1 Acceptance criteria per phase

| Phase | Done when |
| --- | --- |
| 1. Lock manager | Random transaction sequences never violate capacity, FIFO order or token monotonicity |
| 2. Single-node chain | Tampering with any stored block is detected; restart reproduces the same state |
| 3. Consensus | Killing the leader does not lose committed locks and never double-grants |
| 4. Service layer | A client can acquire, wait, be granted by event, release, and survive retries |
| 5. Demos | A live demo runs for ten minutes with fault injection and no violations |
| 6. Evaluation | Charts and a written analysis exist for every claim in the report |

# 7. Evaluation plan

Design the experiments before building so the system exposes the right metrics. Ownership: Ujjwal runs the experiments; Tijay supplies the instrumentation hooks in the lock manager and ledger and checks the results for correctness.

| Experiment | What we vary | What we measure | What to discuss |
| --- | --- | --- | --- |
| Lock latency | Nodes (3, 5, 7); consensus (Raft vs BFT if built) | p50, p95, p99 acquire latency | Cost of fault tolerance and Byzantine protection |
| Throughput | Batch size and timeout; number of clients | Acquire/release ops per second | Where batching stops helping; saturation point |
| Contention | Clients competing for one lock (1 to 100) | Wait time, fairness (grant order), throughput | FIFO behaviour; convoy effects |
| Scalability | Number of shards (optional) | Aggregate throughput | Near-linear scaling for independent locks |
| Baseline comparison | ChainSync, etcd, ZooKeeper, Redis (Redlock), local mutex | Latency and throughput, identical workload | Be honest: we will be slower; explain what the extra cost buys |
| Failover | Kill the leader under load | Recovery time, failed requests, any safety violation | Recovery time vs election timeout |
| Partition tolerance | Cut network 2/1 and 1/1/1 | Availability per side; safety | CP behaviour in practice |
| Lease behaviour | Lease length; client pause length | Reclaim delay; rejected zombie writes | Lease length trade-off |
| Audit overhead | Ledger size over time | Storage growth; proof size and verification time | Cost of immutability; snapshotting |
| Correctness | Random workloads with faults | Violations of mutual exclusion, token order, FIFO; linearizability result | Zero violations is the target; show evidence |

For every experiment record the environment (machine specs, network setup, versions), the workload (clients, think time, lease length), run it several times and report medians and spreads. A figure without these details is not reproducible.

# 8. Failure scenarios we must handle

These are likely examiner questions and also our chaos-test list. See Chapter 19 of the study guide for full answers.

| Scenario | What the design does | Owner of the test |
| --- | --- | --- |
| Lock holder crashes | Lease expires by block time; lock is reclaimed and next waiter promoted | Ujjwal (chaos), Tijay (unit test) |
| Holder is slow, not dead (zombie) | Lease expires; new holder gets a higher token; protected resource rejects the old token | Tijay (T5), Ujjwal (U7) |
| Leader crashes | New leader elected by Raft; committed locks survive; uncommitted requests are retried by the SDK with the same request ID | Ujjwal |
| Network partition | Only the majority side can commit; minority side cannot grant (CP choice) | Ujjwal |
| Client retries / duplicate message | seen set returns the original result; no double effect | Tijay |
| Replay of an old signed transaction | Request IDs and nonces; seen set rejects it | Tijay and Ujjwal |
| Node disagrees on lease expiry | Impossible if only block time is used; leader timestamps validated by followers | Tijay |
| Malicious validator (BFT mode only) | Needs 3f+1 nodes; one liar cannot skew block time or order | Ujjwal (optional) |
| Node restarts | Replay the ledger from storage and reach the identical state | Tijay |

# 9. Working agreement

- Contracts first. Interfaces in proto/ and the consensus interface are changed only after both of us agree.

- Determinism rule (non-negotiable). The lock manager never reads wall-clock time, random numbers, network or files. Only the transaction and block time.

- Branches and reviews. One feature per branch; the other person reviews before merging to main.

- Tests with every change. Lock-manager changes need a property test; consensus changes need a failover test.

- Sync cadence. Short check-in twice a week (what is done, what is blocked, what the other needs). A longer integration session at the end of each phase.

- Balance check. At the end of Phase 3 and Phase 5 compare progress. If one of us is ahead, take over part of the other’s optional work (see section 10) so the load stays even.

- Everyone can defend everything. Each of us reads the other’s half before the viva.

# 10. Optional extensions

Only after the required tasks are done. These need both halves and are the natural place to rebalance.

| Extension | What it adds | Likely owner |
| --- | --- | --- |
| BFT mode (PBFT / CometBFT) | Tolerates malicious validators; swap in behind the consensus interface; adds the 3f+1 experiments | Ujjwal |
| TLA+ specification | Formal proof sketch of mutual exclusion and token monotonicity | Tijay |
| Hybrid locking (Ch. 20) | Machine takes a node-level lease from the chain, local threads share it using fast local locks; far fewer transactions reach the chain | Joint |
| Sharding | Hash lock names across several consensus groups so unrelated locks run in parallel | Ujjwal |
| Snapshots and pruning | Save state periodically and discard old log entries from the working set, keep archive for audit | Tijay |
| Batching tuning | Group requests arriving within a few ms into one block; shows in throughput-vs-latency graph | Ujjwal |

# 11. Risks and open items

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Raft takes longer than planned | Use an existing library first (e.g. hashicorp/raft or etcd/raft) and wrap it in our interface; write our own only if time remains | Ujjwal |
| Mock behaves differently from the real node | Build the mock from the section 3 rules; run the same T8 conformance suite on both | Ujjwal and Tijay |
| Nodes’ states diverge | Replay-determinism test in CI; ban non-deterministic calls in the lock manager | Tijay |
| One half blocks the other | Mock server, stub consensus and dummy state machine let both proceed independently; conformance suite catches mock-vs-real differences | Both |
| Benchmarks show we are far slower than etcd | Expected; frame as the price of trustlessness and auditability, show batching improvements | Ujjwal |
| Scope creep into optional features | Optional list stays closed until the Phase 5 acceptance test passes | Both |

## Decisions to make together

| # | Question | Decide by |
| --- | --- | --- |
| 1 | Implementation language (Python for speed of development, Go for Raft libraries and performance, or a mix) | End of week 1 |
| 2 | Use a Raft library or write our own | End of week 1 |
| 3 | Submission deadline, demo date and viva date, then convert phases to calendar dates | As soon as known |
| 4 | Whether the BFT mode and hybrid locking are in scope | After Phase 4 |
| 5 | REST vs gRPC for the client API | Week 1 |

Source: Blockchain Process Synchronization Study Guide, Chapters 15–24. Chapter numbers in this document refer to that guide.